## Task_Tracker
Task ID | Project Name | Task Name | Assigned To | Start Date | Due Date | Status | Priority
T001 | Website Upgrade | Requirement Gathering | Afreen | 2026-06-01 | 2026-06-03 | Completed | High
T002 | Website Upgrade | UI Design Review | Ali | 2026-06-02 | 2026-06-06 | Completed | Medium
T003 | Website Upgrade | Content Approval | Sara | 2026-06-04 | 2026-06-08 | In Progress | High
T004 | Website Upgrade | Testing | John | 2026-06-05 | 2026-06-10 | Pending | High
T005 | Inventory System | Data Collection | Afreen | 2026-06-01 | 2026-06-04 | Completed | Medium
T006 | Inventory System | Database Setup | Ali | 2026-06-03 | 2026-06-09 | Completed | High
T007 | Inventory System | Dashboard Development | Sara | 2026-06-05 | 2026-06-15 | In Progress | High
T008 | Inventory System | User Testing | John | 2026-06-10 | 2026-06-18 | Pending | Medium
T009 | CRM Migration | Data Cleaning | Afreen | 2026-06-02 | 2026-06-07 | Completed | High
T010 | CRM Migration | Validation | Ali | 2026-06-05 | 2026-06-12 | In Progress | Medium
T011 | CRM Migration | Final Review | Sara | 2026-06-08 | 2026-06-16 | Pending | High
T012 | CRM Migration | Deployment | John | 2026-06-15 | 2026-06-20 | Pending | High
T013 | Vendor Portal | Requirement Analysis | Afreen | 2026-06-01 | 2026-06-05 | Completed | High
T014 | Vendor Portal | Documentation | Ali | 2026-06-04 | 2026-06-08 | Completed | Medium
T015 | Vendor Portal | QA Testing | Sara | 2026-06-07 | 2026-06-14 | In Progress | High
T016 | Vendor Portal | Go Live Support | John | 2026-06-12 | 2026-06-18 | Pending | Medium
T017 | Mobile App | Sprint Planning | Afreen | 2026-06-01 | 2026-06-02 | Completed | High
T018 | Mobile App | Development Tracking | Ali | 2026-06-03 | 2026-06-12 | In Progress | High
T019 | Mobile App | UAT Coordination | Sara | 2026-06-10 | 2026-06-17 | Pending | Medium
T020 | Mobile App | Release Management | John | 2026-06-15 | 2026-06-22 | Pending | High

## Project_Timeline
Task Name | Start Date | Due Date | 2026-06-01 | 2026-06-02 | 2026-06-03 | 2026-06-04 | 2026-06-05 | 2026-06-06 | 2026-06-07 | 2026-06-08 | 2026-06-09 | 2026-06-10 | 2026-06-11 | 2026-06-12 | 2026-06-13 | 2026-06-14 | 2026-06-15 | 2026-06-16 | 2026-06-17 | 2026-06-18 | 2026-06-19 | 2026-06-20 | 2026-06-21 | 2026-06-22
Requirement Gathering | 2026-06-01 | 2026-06-03
UI Design Review | 2026-06-02 | 2026-06-06
Content Approval | 2026-06-04 | 2026-06-08
Testing | 2026-06-05 | 2026-06-10
Data Collection | 2026-06-01 | 2026-06-04
Database Setup | 2026-06-03 | 2026-06-09
Dashboard Development | 2026-06-05 | 2026-06-15
User Testing | 2026-06-10 | 2026-06-18
Data Cleaning | 2026-06-02 | 2026-06-07
Validation | 2026-06-05 | 2026-06-12
Final Review | 2026-06-08 | 2026-06-16
Deployment | 2026-06-15 | 2026-06-20
Requirement Analysis | 2026-06-01 | 2026-06-05
Documentation | 2026-06-04 | 2026-06-08
QA Testing | 2026-06-07 | 2026-06-14
Go Live Support | 2026-06-12 | 2026-06-18
Sprint Planning | 2026-06-01 | 2026-06-02
Development Tracking | 2026-06-03 | 2026-06-12
UAT Coordination | 2026-06-10 | 2026-06-17
Release Management | 2026-06-15 | 2026-06-22

## Dashboard
PROJECT MANAGEMENT DASHBOARD
KPI |  | Status | Count |  | Priority | Count of Priority | Statust with respect to employee
Total Tasks | 20 | Completed | 8 |  | High | 13 | Employee | Completed | In Progress | Pending | Total
Completed | 8 | In Progress | 5 |  | Medium | 7 | Afreen | 5 |  |  | 5
In Progress | 5 | Pending | 7 |  | Grand Total | 20 | Ali | 3 | 2 |  | 5
Pending | 7 | Grand Total | 20 |  |  |  | John |  |  | 5 | 5
Completion % | 40% | [5 empty] | Sara |  | 3 | 2 | 5
[7 empty] | Total | 8 | 5 | 7 | 20
Visualisation